## Sheet1
PLP High Level Work Breakdown structure
Date | Day | Day | Activity | Deliverables | Phase
25th Nov | Friday | Day-1 | 1. Design SRS, HLD,WBS | 1. Understanding document | Requirement
2. Create project folder structure
|  |  | 3. Update time sheet | 2. Updated Time Sheet
3. Minutes of Meeting(one sample)
4. MoM Doc
26th Nov | Saturday | Day-2 |  | 1. Usecase, Class diagram | Design
|  |  | 1. Modify Class Diagram | 2. DB design
2. Create usecase
3. DB Design and Screen Shots.
27th Nov | Monday | Day-3 |  |  | Design
Coding & Self Reviewing
Peer Reviewing
Testing
Presentation
1St Nov - Company Holiday
3rd Nov - The batces will be moving back to ATP